## Project Info
Project Title | Fusion Flavours: A Recipe Book for Cultural Exploration
Group Number | Group 8
Project Description | The idea for a student-focused cookbook originated from an awareness of the challenges that college students encounter, such as little to no prior cooking knowledge, limited funds, and time limits. Given that cooking at home is both economical and healthful, and that students come from a diverse range of backgrounds, this cookbook attempts to empower students to prepare tasty and satisfying meals on their own by offering simple, cost-effective recipes that prioritise nutrition and celebrate cultural diversity.
Included Project Elements (In-Scope) | Development of a comprehensive collection of simple, budget-friendly recipes suitable for university students. Inclusion of recipes that prioritize nutrition, cultural diversity, and ease of preparation. Design and layout of the cookbook, including recipe formatting, photography, and illustrations. Testing and refinement of recipes to ensure accuracy and user-friendliness. Incorporation of cooking tips, nutritional information, and cultural context for each recipe. Promotion and marketing of the cookbook through various channels to reach the target audience of university students.
Excluded Project Elements (Out-of-Scope) | Production and distribution of physical copies of the cookbook (digital format only). Detailed nutritional analysis of each recipe beyond basic information. Customization of recipes for individual dietary needs beyond general options provided. In-depth exploration of advanced cooking techniques or gourmet cuisine. Endorsement or sponsorship by specific brands or products within the cookbook. Long-term tracking of user behavior or impact assessment beyond initial feedback. Translation of the cookbook into multiple languages (initial release in one language only).
Team Member Names | Team Member B, Team Member A

## Work Breakdown Structure (WBS)
TYPE | WBS NUMBER | PRECEDENCE | TASK TITLE | TASK OWNER | COMPLETION STATUS | RISK STATUS | PERCENTAGE COMPLETE | ACCEPTANCE CRITERIA | ASSUMPTIONS AND CONSTRAINTS | STATUS SUMMARY | DURATION (DAYS) | START DATE | DUE DATE | TOTAL COST | FIXED COST | DAILY LABOR COST | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
[47 empty] | July | [30 empty] | August
Indicates whether the task is a Parent or Child task. --------------- Automatically generated; should not be manually edited. | Unique identifier for each task, illustrating the project's hierarchical structure and task relationships. --------------- Automatically generated for parent tasks. | Order in which tasks must be completed, indicating dependencies. --------------- Numeric value. | The title of the task. --------------- Must not be empty. Should be concise and descriptive. | The person responsible for the task. --------------- Updated from Settings sheet. | The current status of task completion. --------------- Select from predefined statuses (e.g., Not Started, In Progress, Completed, On Hold). | Risk status associated with the task. --------------- Select from predefined statuses (e.g., On Track, At Risk, Off Track, N/A). | Percentage of task completion. --------------- Numeric value between 0 and 100. | Criteria for task acceptance. --------------- Descriptive text. Should clearly state specific, measurable, and testable requirements that a deliverable must meet to be considered complete | Assumptions and constraints related to the task. --------------- Descriptive text. Should outline key assumptions and constraints affecting the task. | Summary of the task status. --------------- Descriptive text. Should provide a brief update on the task’s current state. | Calculated number of days the task will take. --------------- Automatically generated. | Planned start date for the task. --------------- Format: YYYY-MM-DD. | Scheduled due date for the task. --------------- Format: YYYY-MM-DD. Should be after the START DATE. | Calculated total cost of the task. --------------- Automatically generated; Numeric value. Should be ≥ 0. Calculated as (DURATION * DAILY RATE) + FIXED COST. | Fixed cost associated with the task. --------------- Numeric value. Should be ≥ 0. | Daily rate for the task, used to calculate total cost. --------------- Numeric value. Should be ≥ 0.
Parent | 1 | 0 | Project Initiation | Team Member B | Completed | On Track | 100 | [6 empty] | 0 | 0 | 0 | bar: 21 to 22
Parent | 2 | 1 | Define Project Scope | Team Member A | Completed | On Track | 100 |  |  |  | 1 | 2024-06-21 | 2024-06-22 | 0 | 0 | 21 | bar: 21 to 22
Child | 1.1.1 | 1.1 | Identify project objectives and goals. | Team Member B | Completed | On Track | 100 | Requirement: Define the overall objectives and specific goals of the project. Measurable: Document primary objectives and some specific goals related to the project's scope and desired outcomes. Testable: Review project documentation to ensure objectives and goals are explicitly stated and align with stakeholder expectations. | Assumptions include stakeholder alignment on project goals. Constraints involve budget limitations and time constraints. | All the requirements, deliverables in this task are completed | 0 | 2024-06-21 | 2024-06-21 | 0 | 0 | 7 | bar: 21
Child | 1.1.2 | 1 | Determine key deliverables. | Team Member A | Completed | On Track | 100 | Requirement: Identify and document all major deliverables that the project is expected to produce. Measurable: List all the deliverables, including detailed descriptions and associated deadlines. Testable: Verify the list of deliverables against project requirements to ensure completeness and relevance, and confirm that each deliverable has a clear and achievable deadline. | Assumptions include clear understanding of deliverable specifications. Constraints involve resource availability and technological limitations. | All the requirements, deliverables in this task are completed | 0 | 2024-06-21 | 2024-06-21 | 0 | 0 | 7 | bar: 21
Child | 1.1.3 | 1.1.1 | Outline project boundaries and constraints. | Team Member B | Completed | On Track | 100 | Requirement: Define the project’s boundaries, including scope inclusions and exclusions, and identify constraints affecting project execution. Measurable: Create a document of all inclusions, exclusions, and any time, budget, or resource constraints. Testable: Cross-check document with project objectives and stakeholder requirements to ensure clarity and understanding. | Assumptions include defined project scope and stakeholder expectations. | All the requirements, deliverables in this task are completed | 0 | 2024-06-22 | 2024-06-22 | 0 | 0 | 7 | bar: 22
Parent | 3 | 1 | Identify Stakeholders | Team Member A | Completed | On Track | 100 |  |  |  | 2 | 2024-06-22 | 2024-06-24 | 7 | 0 | 21 | bar: 22 to 24
Child | 1.2.1 | 1.2 | List all key stakeholders. | Team Member B | Completed | On Track | 100 | Requirement: Identify and document all individuals and groups who have a interest in the project. Measurable: Compile a list that includes all key stakeholders. Testable: Review the stakeholder list to ensure it comprehensively covers all relevant parties involved in or affected by the project, including internal and external stakeholders. | Assumptions: Assumes all relevant stakeholders are identified through initial project scoping. Constraints: Constraints may include limited access to certain stakeholder groups or stakeholders with conflicting interests. | All the requirements, deliverables in this task are completed | 0 | 2024-06-22 | 2024-06-22 | 0 | 0 | 7 | bar: 22
Child | 1.2.2 | 1.2.1 | Define stakeholder roles and responsibilities. | Team Member A | Completed | On Track | 100 | Requirement: Clearly outline the roles and responsibilities of each identified stakeholder. Measurable: Create a roles and responsibilities table that includes specific duties and expectations for each of the ten identified stakeholders. Testable: Cross-check the roles and responsibilities table with stakeholders to confirm accuracy and completeness, and ensure that each stakeholder understands and agrees to their defined role. | Assumptions: Assumes stakeholders are willing and able to fulfill assigned roles and responsibilities. Constraints: Constraints could involve unclear stakeholder expectations or resistance to assigned roles. | All the requirements, deliverables in this task are completed | 0 | 2024-06-23 | 2024-06-23 | 0 | 0 | 7 | bar: 23
Child | 1.2.3 | 1.2 | Conduct stakeholder analysis. | Team Member B | Completed | On Track | 100 | Requirement: Perform an analysis to assess the influence, interest, and impact of each stakeholder on the project. Measurable: Develop a stakeholder analysis report that categorizes stakeholders based on their influence and interest levels, and includes strategies for engagement and communication. Testable: Validate the stakeholder analysis report by reviewing it with the project team. | Assumptions: Assumes accurate assessment of stakeholder influence, interest, and impact based on available information. Constraints: Constraints may include incomplete stakeholder data or difficulty in engaging certain stakeholders effectively. | All the requirements, deliverables in this task are completed | 1 | 2024-06-23 | 2024-06-24 | 7 | 0 | 7 | bar: 23 to 24
Parent | 4 | 1.1 | Conduct Feasibility Study | Team Member A | Completed | On Track | 100 | Requirement: Perform a comprehensive feasibility study to assess various aspects of the project’s viability. Measurable: Produce a feasibility report that covers cost, scalability, flexibility, customization, and time to value, with detailed analysis and findings for each aspect. Testable: Validate the feasibility report by reviewing it with key stakeholders and ensuring all aspects are thoroughly analyzed and conclusions are well-supported by data. | Assumptions: Assumes availability of accurate data for cost estimation, resource assessment, and technical feasibility. Constraints: Constraints could involve budget limitations, resource scarcity, or technological constraints that affect project viability. | All the requirements, deliverables in this task are completed | 1 | 2024-06-24 | 2024-06-25 | 0 | 0 | 0 | bar: 24 to 25
Parent | 5 | 1.3 | Develop Project Charter | Team Member B | Completed | On Track | 100 | Requirement: Create a project charter with purpose, objectives, requirements, stakeholders, constraints, and assumptions. Measurable: The charter should be at least five pages long. Testable: It must be reviewed and approved by the project sponsor and stakeholders. | Assumptions: Assumes consensus among stakeholders on project scope, objectives, and constraints. Constraints: Constraints may include time constraints for charter development, conflicting stakeholder priorities, or organizational policies impacting project scope. | All the requirements, deliverables in this task are completed | 2 | 2024-06-26 | 2024-06-28 | 0 | 0 | 0 | bar: 26 to 28
Parent | 6 | 1.4 | Project Planning | Team Member A | Completed | On Track | 100 |  |  |  | 3 | 2024-06-26 | 2024-06-29 | 0 | 0 | 0 | bar: 26 to 29
Parent | 7 | 2 | Develop Project Plan | Team Member B | Completed | On Track | 100 |  |  |  | 1 | 2024-06-26 | 2024-06-27 | 0 | 0 | 28 | bar: 26 to 27
Child | 2.1.1 | 1.4 | Define project activities and tasks. | Team Member B | Completed | On Track | 100 | Requirement: List all activities and tasks needed to complete the project. Measurable: Document at least 30 tasks with clear descriptions. Testable: Ensure each task is reviewed for necessity and dependencies. | Assumptions: Assumes clarity in project scope and objectives to define detailed activities and tasks. Constraints: Constraints may include limited availability of detailed project requirements or changes in scope affecting task definitions. | All the requirements, deliverables in this task are completed | 0 | 2024-06-26 | 2024-06-26 | 0 | 0 | 7 | bar: 26
Child | 2.1.2 | 2.1.1 | Create a project schedule. | Team Member A | Completed | On Track | 100 | Requirement: Develop a timeline for all tasks and activities. Measurable: Use a Gantt chart to show the schedule. Testable: Verify the schedule includes all tasks and aligns with project deadlines. | Assumptions: Assumes accurate estimation of task durations and dependencies for scheduling. Constraints: Constraints could involve resource availability, unforeseen delays, or changes in project priorities impacting schedule adherence. | All the requirements, deliverables in this task are completed | 0 | 2024-06-26 | 2024-06-26 | 0 | 0 | 7 | bar: 26
Child | 2.1.3 | 2.1.1 | Allocate resources. | Team Member B | Completed | On Track | 100 | Requirement: Assign resources to each task and activity. Measurable: List all resources needed, including people, equipment, and materials. Testable: Ensure resource allocation is reviewed and approved by the project manager. | Assumptions: Assumes availability of required resources as planned. Constraints: Constraints may include resource conflicts, budget limitations, or unexpected resource shortages. | All the requirements, deliverables in this task are completed | 0 | 2024-06-27 | 2024-06-27 | 0 | 0 | 7 | bar: 27
Child | 2.1.4 | 2.1.3 | Develop a budget. | Team Member A | Completed | On Track | 100 | Requirement: Create a detailed project budget. Measurable: Include costs for all resources, tasks, and activities. Testable: Review the budget to ensure it aligns with project requirements. | Assumptions: Assumes accurate cost estimation based on project scope, activities, and resource requirements. Constraints: Constraints could include budget constraints, fluctuating costs of resources. | All the requirements, deliverables in this task are completed | 0 | 2024-06-27 | 2024-06-27 | 0 | 0 | 7 | bar: 27
Parent | 8 | 2 | Risk Management Plan | Team Member B | Completed | On Track | 100 |  |  |  | 1 | 2024-06-28 | 2024-06-29 | 0 | 0 | 21 | bar: 28 to 29
Child | 2.2.1 | 2.1.1, 2.1.4 | Identify potential project risks. | Team Member A | Completed | On Track | 100 | Specific: Identify and document potential risks relevant to the project requriments. | Assumptions: Assumes thorough identification of risks across project aspects. Constraints: Constraints may include limited data for risk assessment. | All the requirements, deliverables in this task are completed | 0 | 2024-06-28 | 2024-06-28 | 0 | 0 | 7 | bar: 28
Child | 2.2.2 | 2.2.1 | Assess risk impact and likelihood. | Team Member B | Completed | On Track | 100 | Specific: Assess the impact of each identified risk | Assumptions: Assumes accurate assessment of risk severity and probability. Constraints: Constraints could involve subjective risk assessment. | All the requirements, deliverables in this task are completed | 0 | 2024-06-29 | 2024-06-29 | 0 | 0 | 7 | bar: 29
Child | 2.2.3 | 2.2.1 | Develop risk mitigation strategies. | Team Member A | Completed | On Track | 100 | Specific: Develop actionable mitigation strategies for each identified risk. Measurable: Specify clear milestones or actions for each strategy, including responsibilities and timelines. | Assumptions: Assumes proactive planning to reduce risk impact. Constraints: Constraints may include resource limitations impacting strategy implementation. | All the requirements, deliverables in this task are completed | 0 | 2024-06-29 | 2024-06-29 | 0 | 0 | 7 | bar: 29
Parent | 9 | 2024-02-01 | Cook Book Creation | Team Member B | Completed | On Track | [7 empty] | 0 | 0 | 0 | bar: 15 to 5
Parent | 10 | 3 | Reserch & Content Development | Team Member A | Completed | On Track |  |  |  |  | 20 | 2024-07-11 | 2024-07-31 | 489 | 300 | 42 | bar: 11 to 31
Child | 3.1.1 | 3.1.1 | Interacting with people/students for collecting different cultural recipes | Team Member B | Completed | On Track | 100 | Requirement: Engage with diverse groups to gather recipes representing various cultures. Measurable: Aim to collect at least 10 unique recipes from different cultural backgrounds. Testable: Validate recipe authenticity through community validation. | Assumptions: Assumes willingness and availability of diverse individuals to share authentic recipes. Constraints: Constraints may include language barriers or logistical challenges in scheduling interviews. | From this task the schedule was delayed and we had to change dates. This task didn't go as planned so we have collected recipes from the internet. | 3 | 2024-07-11 | 2024-07-14 | 21 | 0 | 7 | bar: 11 to 14
Child | 3.1.2 | 3.1.3 | Develop cultural context and background for each recipe. | Team Member A | Completed | On Track | 100 | Specific: Provide historical, geographical, and social context for each recipe. Measurable: Include at least 200 words of context per recipe. Testable: Ensure accuracy and relevance of cultural information through peer review or consultation. | Assumptions: Assumes access to accurate cultural information through research or expert consultation. Constraints: Constraints could include limited availability of historical or cultural data for some recipes. | We have developed cultural recipes for all the dishes that we want to add in the cook book. In total there are 7 recipes which are Non-veg and also same recipes in vegetarian. We have also included 5 fusion Recipes for Non-Vegetarian. | 4 | 2024-07-15 | 2024-07-19 | 28 | 0 | 7 | bar: 15 to 19
Child | 3.1.3 | 3.1.1 | Creating, Developing and testing of Recipes | Team Member B | Completed | On Track | 100 | Specific Requirements: Develop at least five new recipes that align with the theme of cultural exploration and fusion. Measurable Requirements: Each recipe must be tested and refined a minimum of three times to ensure consistency and quality. Testable Requirements: Recipes must be reviewed by at least two team members and receive positive feedback before being finalized. | Assumptions:All necessary kitchen equipment and tools are available for recipe development and testing. Team members have the required culinary skills and knowledge to create and refine recipes. Constraints: Limited budget for purchasing ingredients and conducting multiple tests. Time constraints for developing and testing recipes, which may impact the number of iterations possible. Potential dietary restrictions and allergies of team members or test groups. Limited access to some specialized or rare ingredients, which may require substitutions. | We are not able to do this task because of the time constraints. | 6 | 2024-07-19 | 2024-07-25 | 242 | 200 | 7 | bar: 19 to 25
Child | 3.1.4 | 3.1.6 | Surveying grocery markets | Team Member A | Completed | On Track | 100 | Specific Requirements: Identify and source ingredients from at least three different suppliers for each recipe. Measurable Requirements: Provide a detailed report on the availability, quality, and cost of ingredients from each supplier. Testable Requirements: Ensure the sourced ingredients meet the quality standards set for the recipe, verified through taste tests and quality checks. | Assumptions:The market survey will be conducted within specific groceries stores to ensure ingredient availability. | We got prices for the ingredients that we will need for most recipes | 2 | 2024-07-15 | 2024-07-17 | 114 | 100 | 7 | bar: 15 to 17
Child | 3.1.5 | 3.1.3 | Collecting good photos for the recipes | Team Member B | Completed | On Track | 100 | Specific: Capture high-quality images that showcase the preparation and final presentation of each dish. Measurable: Aim for at least one visually appealing photo per recipe. Testable: Evaluate photos based on composition, lighting, and appeal to enhance visual storytelling. | Assumptions: Assumes access to suitable photography equipment and settings for food presentation. Constraints: Constraints could include lighting issues or aesthetic challenges in capturing appetizing images. | We have started collecting photos from the internet. | 6 | 2024-07-19 | 2024-07-25 | 42 | 0 | 7 | bar: 19 to 25
Child | 3.1.6 | 3.1.5 | Write Detailed recipe instructions | Team Member A | Completed | On Track | 100 | Specific: Create step-by-step instructions that are clear and easy to follow. Measurable: Include cooking times, serving sizes, and ingredient quantities for each recipe. Testable: Test recipes with individuals unfamiliar with the cuisine to verify clarity and completeness of instructions. | Assumptions: Assumes clear understanding of cooking techniques and ingredient measurements. Constraints: Constraints may include variations in cooking methods or ingredient availability affecting recipe consistency. | All the recipes have detailed instructions ready and the task is completed. | 6 | 2024-07-25 | 2024-07-31 | 42 | 0 | 7 | bar: 25 to 31
Parent | 11 | 3 | Graphic Design & Layout | Team Member B | Completed | On Track |  |  |  |  | 21 | 2024-07-15 | 2024-08-05 | 112 | 0 | 28 | bar: 15 to 5
Child | 3.2.1 | 3.2.1 | Analyzing which online platform to use for creation of cook book | Team Member A | Completed | On Track | 100 | Specific: Evaluate and select an online platform based on usability, customization options, cost-effectiveness, and positive user reviews. Measurable: Choose a platform rated at least 4 stars for user interface and integration capabilities. Testable: Test platform features by uploading sample content to ensure compatibility and ease of use. | Assumptions: Assumes availability of platforms with suitable features like recipe management and customization. Constraints: Constraints may include budget limitations or technical compatibility issues with chosen platform. | We have finalized to use canva online website for desiging the cook book. | 2 | 2024-07-15 | 2024-07-17 | 14 | 0 | 7 | bar: 15 to 17
Child | 3.2.2 | 3.1.3, 3.1.2 | Designing and layouting all the recipes in cook book | Team Member B | Completed | On Track | 100 | Specific: Create a uniform layout for recipes with consistent fonts, spacing, and structure. Measurable: Ensure each recipe includes a high-quality image and follows a standardized format. Testable: Review layout prototypes with stakeholders to confirm readability and adherence to design standards. | Assumptions: Assumes access to design tools for creating consistent and visually appealing layouts. Constraints: Constraints could include time constraints or design preferences that vary across recipes. | We are using a template and the layout of the book is ready. | 4 | 2024-08-01 | 2024-08-05 | 28 | 0 | 7 | bar: 1 to 5
Child | 3.2.3 | 3.1.4 | Adding images to all the recipes | Team Member A | Completed | On Track | 100 | Specific: Source or create visually appealing images that enhance each recipe presentation. Measurable: Include at least one high-resolution image per recipe that illustrates key preparation steps or final dish presentation. Testable: Gather feedback on image quality and relevance to ensure they enhance visual appeal and cultural authenticity. | Assumptions: Assumes availability of high-quality images that enhance recipe presentation. Constraints: Constraints may include copyright issues or aesthetic challenges in sourcing suitable images. | The task is completed. | 4 | 2024-08-01 | 2024-08-05 | 28 | 0 | 7 | bar: 1 to 5
Child | 3.2.4 | 3.2.3 | Creating a cover page for the cook book | Team Member B | Completed | On Track | 100 | Specific: Design a cover page that reflects the cookbook's cultural theme and content. Measurable: Include essential elements such as title, subtitle, author name, and culturally relevant imagery. Testable: Validate cover page designs with stakeholders and target audience to ensure attractiveness and alignment with project goals. | Assumptions: Assumes creative freedom to design a cover page that aligns with cookbook theme and audience expectations. Constraints: Constraints could include limited design resources or conflicting feedback from stakeholders on cover design preferences. | The task is completed. | 6 | 2024-07-21 | 2024-07-27 | 42 | 0 | 7 | bar: 21 to 27
Parent | 12 | 3 | Content Review and editing | Team Member A | Completed | On Track | 0 |  |  |  | 2 | 2024-08-05 | 2024-08-07 | 14 | 0 | 21 | bar: 5 to 7
Child | 3.3.1 | 3.2.2 | Review content for accuracy and completeness. | Team Member B | Completed | On Track | 100 | Specific: Verify that all information is correct and all required details are included. Measurable: Cross-check content against reliable sources or subject matter experts. Testable: Conduct content review sessions with experts or stakeholders for validation. | Assumptions: Assumes content is based on reliable sources or subject matter experts. Constraints: Constraints may include time constraints for thorough content review. | We reviewed the contents of the book for its accuracy and completeness. | 2 | 2024-08-05 | 2024-08-07 | 14 | 0 | 7 | bar: 5 to 7
Child | 3.3.2 | 3.3.1 | Edit text for clarity and consistency. | Team Member A | Completed | On Track | 100 | Specific: Ensure text is clear, concise, and follows a consistent style. Measurable: Use readability tools to assess text complexity and coherence. Testable: Request feedback from friends, peers and faculty. | Assumptions: Assumes clarity in conveying information and maintaining a consistent style. Constraints: Constraints could involve subjective interpretations of clarity or consistency. | This task is completed. We edited the book to make it more correct | 0 | 2024-08-06 | 2024-08-06 | 0 | 0 | 7 | bar: 6
Child | 3.3.3 | 3.3.2 | Proofread for grammatical and typographical errors. | Team Member B | Completed | On Track | 100 | Specific: Correct any grammar, spelling, or punctuation mistakes. Measurable: Use proofreading software to catch errors and inconsistencies. Testable: Perform final review rounds to eliminate errors before publication. | Assumptions: Assumes use of proofreading tools for accurate error detection. Constraints: Constraints may include oversight of minor errors or time limitations for comprehensive proofreading. | Task is completed successfully | 0 | 2024-08-06 | 2024-08-06 | 0 | 0 | 7 | bar: 6
Parent | 13 | 4 | Marketing | Team Member A | Not Started | N/A | 20 |  |  | No started |  |  |  | 0 | 0 | 0
Parent | 14 | 3, 3.2, 3.3 | Develop Marketing Strategy | Team Member B | Not Started | N/A | 20 |  |  | No started | 39 | 2024-06-22 | 2024-07-31 | 42 | 0 | 21 | bar: 22 to 31
Child | 4.1.1 | 4.1 | Identify target audience. | Team Member A | Not Started | N/A | 0 | Specific: Determine demographics and preferences of potential cookbook buyers. Measurable: Define audience segments based on age, interests, and cultural affinity. | Assumptions: Assumes understanding of demographics and preferences through market research or analytics. Constraints: Constraints may include limited access to specific audience segments or evolving consumer behaviors. | We have identified our target audience which are students who will be majorly benefitied with this project | 2 | 2024-06-22 | 2024-06-24 | 14 | 0 | 7 | bar: 22 to 24
Child | 4.1.2 | 4.1.1 | Define marketing objectives and goals. | Team Member B | Not Started | N/A | 0 | Specific: Set clear goals such as increasing cookbook sales. Measurable: Establish metrics students giving feedbacks via google forms. Testable: Monitor progress regularly to ensure goals are achievable and aligned with business outcomes. | Assumptions: Assumes alignment of objectives with business goals such as sales growth or brand awareness. Constraints: Constraints could include competitive pressures or economic factors impacting goal achievement. | We have identified the objectives and goals and the task is completed. | 1 | 2024-06-23 | 2024-06-24 | 7 | 0 | 7 | bar: 23 to 24
Child | 4.1.3 | 4.1 | Develop marketing message | Team Member A | Not Started | N/A | 0 | Specific: Craft a compelling message highlighting cultural diversity and culinary exploration. Measurable: Ensure message resonates with target audience emotions and values. Testable: Test message effectiveness by requesting feedback. | Assumptions: Assumes creation of compelling messaging that resonates with target audience emotions and values. Constraints: Constraints may involve message testing for effectiveness or adapting messages across different marketing channels. | No started | 3 | 2024-07-28 | 2024-07-31 | 21 | 0 | 7 | bar: 28 to 31
Parent | 15 | 4.2 | Creating Marketing Materials | Team Member B | Not Started | N/A | 0 |  |  | No started | 2 | 2024-08-01 | 2024-08-03 | 108 | 80 | 14 | bar: 1 to 3
Child | 4.2.1 | 4.2.2 | Design promotional graphics and images. | Team Member A | Not Started | N/A | 0 | Specific: Create visually appealing graphics that showcase cookbook themes and recipes. Measurable: Ensure graphics align with brand aesthetics and enhance engagement. Testable: Review feedback on graphic impact from target audience and stakeholders. | Assumptions: Assumes access to design tools and creative expertise for visually appealing content. Constraints: Constraints may include time constraints for graphic creation or budget limitations for professional design services. | No started | 2 | 2024-08-01 | 2024-08-03 | 44 | 30 | 7 | bar: 1 to 3
Child | 4.2.2 | 4.1.3 | Develop content for marketing campaigns (e.g., blog posts, social media posts, email newsletters). | Team Member B | Not Started | N/A | 0 | Specific: Write engaging content for blogs, social media, and email newsletters. Measurable: Include key messages about cultural diversity and culinary exploration. Testable: Analyze campaign performance metrics to refine content strategy and improve effectiveness. | Assumptions: Creation of engaging content aligned with campaign objectives and audience preferences. Constraints: This could include content distribution challenges or compliance with platform guidelines. | No started | 2 | 2024-08-01 | 2024-08-03 | 64 | 50 | 7 | bar: 1 to 3
Parent | 5 | 5 | Monitor & Analyze | Team Member B | Completed | On Track | 100 |  |  | No started | 9 | 2024-08-07 | 2024-08-16 | 63 | 0 | 7 | bar: 7 to 16
Child | 5.1 | 4.2 | Adding google form link at the end of the book for user feedback and monitoring the success | Team Member A | Completed | On Track | 100 | Specific: Include a Google Form link to gather reader feedback on cookbook content and usability. Measurable: Track responses to assess user satisfaction and identify areas for improvement. Testable: Review feedback regularly to make data-driven decisions for future editions or promotions. | Assumptions: Assumes effective integration of the Google Form link to gather user feedback. Constraints: Constraints may include user engagement with feedback forms or data privacy considerations. | We collected the feedbacks from the students and by the responses we observed that many people enjoyed reading the cultural stories and recipes for it. | 9 | 2024-08-07 | 2024-08-16 | 63 | 0 | 7 | bar: 7 to 16

## Definitions
TYPE | WBS NUMBER
PRECEDENCE | TASK TITLE
TASK TITLE | TASK OWNER
RISK STATUS | COMPLETION STATUS
Risk Status: This describes the potential for problems or setbacks that could affect the project's success. | Completion Status: This indicates how far along the project is towards its final goals.
On Track: No major risks are currently identified. The task is proceeding as planned. At Risk: Potential issues have been flagged that could cause delays or changes if they occur. Off Track: Significant problems or risks have materialized, and they are actively impacting the task's progress. N/A: Not applicable. This status might be used if the task is too early in its stages for risk assessment. | Not Started: The project is in the planning phase, and active work hasn't begun. In Progress: The task is actively underway and progressing Completed: The task has been finished successfully. On Hold: Work on the project has temporarily stopped due to unforeseen circumstances or a strategic decision.
ACCEPTANCE CRITERIA | PERCENTAGE COMPLETE
Acceptance Criteria: Clear, specific, and measurable standards that a task's output (deliverable) must satisfy before it can be considered completed and accepted by stakeholders. | A numerical representation of how much of a task has been accomplished, expressed as a value between 0% (not started) and 100% (completed). Gives a quick overview of progress at a glance over time.
Example: Task - Design a new website landing page Acceptance Criteria: - The page loads within 3 seconds on a standard internet connection. - All main call-to-action buttons are prominently displayed above the fold. - The page design is mobile-responsive and displays correctly on various screen sizes. - The page incorporates the company's branding guidelines (logo, color palette, fonts). Example: Task - Implement a new employee onboarding process Acceptance Criteria: - A comprehensive onboarding checklist is created, outlining all required steps and tasks. - New employee welcome packet is drafted, including company information, policies, and benefits. | Examples: Task: Write a project report Percentage Complete: 50% (half of the report is written) Task: Design a new product logo Percentage Complete: 85% (nearly finished, just some minor revisions remaining) Task: Conduct market research for a new service Percentage Complete: 100% (all research tasks are finished)
RISK STATUS | ASSUMPTIONS AND CONSTRAINTS
Risk Status: This describes the potential for problems or setbacks that could affect the project's success. | Assumptions: Factors or conditions that are believed to be true, but may not be definitively proven, and upon which the project or task relies. Constraints: Limitations or restrictions (often related to time, budget, resources, or scope) that can affect the project or task's execution
On Track: No major risks are currently identified. The task is proceeding as planned. At Risk: Potential issues have been flagged that could cause delays or changes if they occur. Off Track: Significant problems or risks have materialized, and they are actively impacting the task's progress. N/A: Not applicable. This status might be used if the task is too early in its stages for risk assessment. | Example: Task - Organize a company-wide training workshop Assumptions: - All registered employees will attend the workshop. - The training venue will have adequate audio/visual equipment. Constraints: - The budget for the workshop is $5,000. - The workshop must be completed within two weeks.
COMPLETION STATUS | STATUS SUMMARY
Completion Status: This indicates how far along the project is towards its final goals. | A concise overview of the current state of a task, highlighting its progress, key milestones, upcoming activities, and any potential issues or risks.
Not Started: The project is in the planning phase, and active work hasn't begun. In Progress: The task is actively underway and progressing Completed: The task has been finished successfully. On Hold: Work on the project has temporarily stopped due to unforeseen circumstances or a strategic decision. | Example: Task - Develop a marketing campaign for a new product Status Summary: - Market research completed; target audience identified. - Creative briefs drafted; awaiting approval. - Finalize creative assets; scheduled media placements. - Potential delays in obtaining regulatory approval for ad content.
FIXED COST | DAILY LABOUR COST
A fixed cost is an expense that remains constant regardless of the level of activity or output related to a task. | How to Estimate: Hourly Rate: Start by determining your desired hourly rate. This can be based on your experience, skills, industry standards, or the value you bring to a task. Working Hours: Estimate the number of hours you spend in a day doing the task. This includes both direct work on tasks and indirect activities like meetings, communication, and planning. Calculation: Multiply your hourly rate by the number of working hours to get your estimated daily labor cost.
Example Task: Rent a venue for a conference Fixed Cost: The rental fee for the venue is $500. Task: Purchase software licenses for a team Fixed Cost: The cost of the software licenses is $100. | Example: Hourly Rate: $5 Daily Working Hours: 7 hours DAily Labor Cost: $50/hour * 7 hours = $35